## Implementation Tracker
Metric | Value
Total Activities | 69
Completed | 0
In Progress | 0
Not Started | 69
How to use | Enter progress as a percentage, e.g. 25%, 70% or 100%.
Completion indicator | At 100%, the Completion column automatically shows a green ✓-Completed, ~ In Progress ; otherwise it shows ○.
MAIN ACTIVITY | Sub-Activity | Implementation | Status in Percentage | Start Date | End Date | Responsible Personnel | Completion
1. Reference Data & Configuration | Configure Facility Mapping | Maintain mapping between GOTHOMIS HFR facility codes and the corresponding Afya Maoni facility codes. | 0% |  |  | Integration / Business | o - Not Started
| Configure Service Point Codes | Maintain agreed OPD, IPD, RCH, LAB, PHA, EMD and additional service-point mappings. | 0% |  |  | Integration / Business | o - Not Started | 6
| Configure Type of Care Codes | Maintain agreed mappings for OUTPATIENT, INPATIENT, ANC, PNC, FP and additional care values. | 0% |  |  | Integration / Business | o - Not Started
| Configure Feedback Channels | Maintain the agreed feedback channels, including IVR and WhatsApp. | 0% |  |  | Afya Maoni / Business | o - Not Started
2. Client Consent & Eligibility | Capture Feedback Consent | Record whether the client agrees to be contacted for feedback. | 0% |  |  | GOTHOMIS Backend / Business | o - Not Started
| Consent Validation | Share visit information only when Consent Status is true. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Client Opt-Out | Respect withdrawal of consent and prevent subsequent feedback contact. | 0% |  |  | Backend / Business | o - Not Started
| Phone Number Validation | Validate eligible client mobile numbers before transmission. | 0% |  |  | GOTHOMIS Backend | o - Not Started
3. Visit Data Exchange | Visit Integration API | Implement GOTHOMIS transmission of eligible visit information to Afya Maoni through the integration gateways. | 0% |  |  | Backend / Integration | o - Not Started
| Facility Information | Send the HFR facility identifier associated with the visit. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Client Demographics | Send age, sex and applicable pregnancy status. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Service Point Visit | Send service points visited during the encounter. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Visit Identification | Send MRN and unique Visit ID for linkage and duplicate detection. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Type of Care | Send applicable care values recorded during the visit. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Visit Date | Send visit date and time using the agreed ISO 8601 format. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Visit Trigger | Automatically initiate the integration at the agreed point in the client visit workflow. | 0% |  |  | GOTHOMIS Backend / Business | o - Not Started
4. Afya Maoni Survey Initiation | Visit Acknowledgement | Return an acknowledgement after successful receipt and validation of visit information. | 0% |  |  | Afya Maoni Backend | o - Not Started
| SMS Invitation | Send an SMS invitation to eligible clients after receiving visit information. | 0% |  |  | Afya Maoni | o - Not Started
| IVR Survey Initiation | Allow invited clients to initiate the feedback survey through IVR. | 0% |  |  | Afya Maoni | o - Not Started
| WhatsApp Survey Initiation | Allow invited clients to initiate the feedback survey through WhatsApp. | 0% |  |  | Afya Maoni | o - Not Started
| Survey Continuation | Continue the survey without repeating valid information already supplied by GOTHOMIS. | 0% |  |  | Afya Maoni / Business | o - Not Started
| Remaining Questions | Ask unanswered applicable questions, including education level and travel time. | 0% |  |  | Afya Maoni / Business | o - Not Started
5. Feedback Exchange to GOTHOMIS | Feedback API | Implement transmission of completed Afya Maoni feedback to GOTHOMIS. | 0% |  |  | Backend / Integration | o - Not Started
| Feedback-to-Visit Linkage | Link returned feedback to the original Visit ID and MRN. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Feedback Identification | Capture the unique Feedback ID for each returned feedback record. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Response Date | Capture the date and time when feedback was completed. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Feedback Channel | Capture the channel used to submit feedback. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Overall Satisfaction | Capture the client's overall satisfaction response. | 0% |  |  | GOTHOMIS Backend / Business | o - Not Started
| Survey Responses | Store question codes, questions and client responses. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Client Comments | Store optional free-text feedback comments. | 0% |  |  | GOTHOMIS Backend | o - Not Started
| Feedback Display (score card) | Display returned feedback in GOTHOMIS for authorised facility teams. | 0% |  |  | Frontend / Backend | o - Not Started
6. Validation & Error Handling | Payload Validation | Validate required fields, formats and agreed code values. | 0% |  |  | Backend / Integration | o - Not Started
| HTTP Response Handling | Implement agreed success and error response handling. | 0% |  |  | Backend / Integration | o - Not Started
| Retry Mechanism | Retry eligible 429, 500, 503 and timeout failures. | 0% |  |  | Backend / Integration | o - Not Started
| Retry Schedule | Apply the agreed 1, 5 and 15 minute retry intervals, respecting Retry-After for 429. | 0% |  |  | Backend / Integration | o - Not Started
| Failed Records Queue | Queue transactions that remain unsuccessful after the final retry. | 0% |  |  | Backend / DevOps | o - Not Started
| Duplicate Visit Handling | Prevent duplicate visit processing using Visit ID. | 0% |  |  | Backend | o - Not Started
| Duplicate Feedback Handling | Prevent duplicate feedback processing using Feedback ID. | 0% |  |  | Backend | o - Not Started
| Conflict Handling | Return and review 409 conflicts when the same identifier arrives with different content. | 0% |  |  | Backend / Integration | o - Not Started
7. Security & Privacy | HTTPS/TLS Security | Enforce HTTPS using TLS 1.2 or higher for all integration traffic. | 0% |  |  | DevOps / Security | o - Not Started
| API Authentication | Implement the agreed authentication through HIM and Muungano Gateway. | 0% |  |  | Backend / Security | o - Not Started
| Environment Credentials | Maintain separate credentials for sandbox and production environments. | 0% |  |  | DevOps / Security | o - Not Started
| IP Allowlisting | Restrict API access to approved source IP addresses. | 0% |  |  | DevOps / Security | o - Not Started
| Data Encryption | Protect personal and health information in transit and at rest. | 0% |  |  | Security / DevOps | o - Not Started
| Secure Logging | Prevent full personal-data payloads from being stored in integration logs. | 0% |  |  | Backend / Security | o - Not Started
| Access Control | Restrict access to feedback and integration data to authorised personnel. | 0% |  |  | Security / Business | o - Not Started
| Data Retention Rules | Agree and implement retention/anonymisation periods for contact details and feedback records. | 0% |  |  | Business / Security | o - Not Started
8. Audit, Monitoring & Reconciliation | Transaction Logging | Log request ID, timestamp, HTTP status and processing duration. | 0% |  |  | Backend / DevOps | o - Not Started
| Integration Audit Trail | Maintain traceability of visit and feedback exchanges. | 0% |  |  | Backend / Security | o - Not Started
| Failed Transaction Monitoring | Monitor failed integration transactions for investigation. | 0% |  |  | DevOps / Support | o - Not Started
| Transaction Reconciliation | Reconcile GOTHOMIS and Afya Maoni transactions using Visit ID and Feedback ID. | 0% |  |  | Integration / Support | o - Not Started
| Transaction Count Monitoring | Compare daily transaction volumes between participating systems. | 0% |  |  | DevOps / Support | o - Not Started
| API Availability Monitoring | Monitor APIs against the agreed 99.5% monthly availability target. | 0% |  |  | DevOps | o - Not Started
| Maintenance Notification | Support at least 48 hours' notice for planned maintenance. | 0% |  |  | PM / DevOps | o - Not Started
9. Integration Testing & UAT | Sandbox Configuration | Configure the integration sandbox using non-production client data. | 0% |  |  | DevOps / Integration | o - Not Started
| Visit API Testing | Test valid, invalid and incomplete visit payloads. | 0% |  |  | QA / Backend | o - Not Started
| Consent Testing | Verify that only consented clients are transmitted. | 0% |  |  | QA / Business | o - Not Started
| Duplicate Testing | Test duplicate Visit ID and Feedback ID scenarios. | 0% |  |  | QA / Backend | o - Not Started
| IVR Journey Testing | Test the complete client feedback journey through IVR. | 0% |  |  | QA / Afya Maoni | o - Not Started
| WhatsApp Journey Testing | Test the complete client feedback journey through WhatsApp. | 0% |  |  | QA / Afya Maoni | o - Not Started
| Care Mapping Testing | Validate type-of-care and survey-question mappings. | 0% |  |  | QA / Business | o - Not Started
| Feedback Linkage Testing | Verify feedback is returned against the correct source visit. | 0% |  |  | QA / Integration | o - Not Started
| End-to-End Testing | Test GOTHOMIS → Afya Maoni → SMS → IVR/WhatsApp → GOTHOMIS flow. | 0% |  |  | QA / Integration | o - Not Started
| UAT Sign-Off | Obtain written approval from both parties before production release. | 0% |  |  | PMORALG / MOH / QA | o - Not Started
10. Deployment & Support | Production Configuration | Configure approved production endpoints and credentials. | 0% |  |  | DevOps / Security | o - Not Started
| Production Deployment | Deploy the approved integration to the production environment. | 0% |  |  | DevOps / Integration | o - Not Started
| Post-Go-Live Validation | Validate transactions and feedback linkage after production deployment. | 0% |  |  | QA / Integration | o - Not Started
| Technical Support Contacts | Maintain designated GOTHOMIS and Afya Maoni technical support contacts. | 0% |  |  | PMORALG / MOH | o - Not Started
| Operational Handover | Hand over monitoring, reconciliation and incident procedures to support teams. | 0% |  |  | PM / Support | o - Not Started

## Summary
Afya Maoni & GoTHOMIS Integration – Progress Summary
Metric | Value
Total Activities | 69
Completed | 0
In Progress | 0
Not Started | 69
How to use | Enter progress as a percentage, e.g. 25%, 70% or 100%.
Completion indicator | At 100%, Completion shows ✓ - Completed; between 1% and 99% it shows ~ In Progress; otherwise ○ - Not Started.